## Open Action Items
1.12 Software Defined Radio Open Action Items
2018-10-31 | Last Update
Date | Description | DRI | Due By | #D | Notes / Comments
2018-10-24 | Updating simulations of analog components with most recent information from research | Samual Hussey | 2018-11-01 | 1 | Working with Zackary to update simulations
2018-10-24 | Labor Cost Schedule | James Bell | 2018-11-18 | 18 | This is a class deliverable
2018-10-10 | Understand the fundamentals of digital signal processing within the bounds of our design and project. | James Bell | 2018-11-22 | 22 | My goal is to be able to completely understand the data flow and processing for the desgin. This will take longer then first thought
2018-10-03 | Ordering Parts | James Bell | 2018-10-28 | - | Completed - Fill out and submit paperwork for ordering parts.
2018-10-10 | Working on RF Ampligier and Bandpass filter design as our simulations and test for the amplifier design did not meet our needs. | Zachary Schneiderman | 2018-10-22 | - | Review/ redesign our bandpass filters and amplifer.
# items | Team Member
3 | James Bell
1 | Samual Hussey
1 | Zachary Schneiderman
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Closed Action Items
1.12 Software Defined Radio Open Action Items
2018-09-10 | Today's Date
Date | Description | DRI | Due By | #D | Notes / Comments
2018-08-31 | Gather contact information for each member of the team | James Bell | 2018-09-01 | - | CLOSED: It was done and we now have clear methods of communication
2018-08-31 | Create a github for repository of documentation and information | Zachary Schneiderman | 2018-09-10 | 0 | CLOSED: Done on 9/5/2018 and in use currently.
2018-08-31 | Rough draft of assigned sections in statement of work | James Bell | 2018-09-12 | - | CLOSED: Done on 9/12/2018.
2018-08-31 | Rough draft of assigned sections in statement of work | Samual Hussey | 2018-09-12 | - | CLOSED: Done on 9/12/2018.
2018-08-31 | Rough draft of assigned sections in statement of work | Zachary Schneiderman | 2018-09-12 | - | CLOSED: Done on 9/12/2018.
2018-08-31 | Watch and take notes of videos for SDR Prototype | James Bell | 2018-09-14 | - | CLOSED: Done on 9/14/2018.
2018-08-31 | Watch and take notes of videos for SDR Prototype | Samual Hussey | 2018-09-14 | - | CLOSED: Done on 9/14/2018.
2018-08-31 | Watch and take notes of videos for SDR Prototype | Zachary Schneiderman | 2018-09-14 | - | CLOSED: Done on 9/14/2018.
2018-09-12 | Organizing, and commenting pre-existing code for Prototype | James Bell | 2018-10-18 | - | CLOSED:
2018-09-12 | Schematics for Prototype in multi-sim or other such software | Samuel Hussey | 2018-10-22 | - | CLOSED: Completed for analog components we are biulding
2018-09-12 | List of components in Prototype priced and deliver estimates | Zachary Schneiderman | 2018-10-22 | - | CLOSED: Compiling list
2018-10-03 | Ordering Parts | James Bell | 2018-10-28 | - | CLOSED: Completed - Fill out and submit paperwork for ordering parts.
# items | Team Member
3 | James Bell
2 | Samual Hussey
3 | Zachary Schneiderman
0 | 0
Note on A2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Instructions and Lists
Team Members
James Bell
Samual Hussey
Zachary Schneiderman
The DRI field uses the Data > Data Validation function in Excel, this allows you to quickly select the team members names. Change the names above to match your team.
If you copy and paste the last action item it will likely mess up the formulas below. Try inserting a row above then pasting the last row into the added row.
You can use the Data > Sort & Filter > Filter function on the row headings if you want to sort by DRI or due date. Same issue applies as above, have to be careful about adding rows below areas that are used in formulas.
Having column A blank makes it easier to capture a screenshot to paste in weekly. Also you can go into view and turn off gridlines if you want a cleaner look.