## Sheet1
Labor Estimate
| Radio Freqency Design Engineer | Lawyer specializing in The FCC | Digital Signal Processing Engineer | Test Engineer | Technical Writer | Technician | Fabricator/Assembler | Drafting/CAD | Marketing Analyst | Management/Supervison | Cleaning/ Janitorial services | Total cost per stage
Burdened Hourly Rate | 77.06 | 114.63 | 82.55 | 63.8 | 70.35 | 41.17 | 30.77 | 52.16 | 60.15 | 64.44 | 27.71
Task | Hours Required
Project Definition | 40 | 40 | [6 empty] | 10 | 22.5 |  | 9719
Legal documents | 4 | 60 | [6 empty] | 4 | 17 |  | 8522.12
Functional Specification | 40 | 4 | 40 |  | 8 |  |  | 10 |  | 25.5 |  | 9570.54
Simulations | 10 |  | 40 | 6 | [5 empty] | 14 |  | 5357.56
Test Plan | 20 |  | 20 | 40 | 8 |  |  |  |  | 22 |  | 7724.68
Prototype Assembly | [5 empty] | 16 | 20 |  |  | 9 |  | 1854.08
Characterization | 10 |  |  | 40 | [5 empty] | 12.5 |  | 4128.1
User Manual |  | 4 |  |  | 10 |  |  | 30 | 10 | 13.5 |  | 4198.26
Cleaning Services | [10 empty] | 34 | 942.14
[9 empty] | Total Burdened Cost = |  |  | 52016.48
Total number of hours in project = |  |  | 680