## Open Action Items
1.12 Software Defined Radio Open Action Items
2019-02-04 | Last Update
Date | Description | DRI | Due By | Notes / Comments
2019-01-28 | Combine audio transformer and low pass filter | James Bell | 2019-02-04 | Completed - simple soldering
2019-01-28 | RF splitter and combiner | James Bell | 2019-02-06 | It is a doubled wrapped torroid
2019-01-28 | Bandpass filters | Samual Hussey | 2019-02-13
2019-02-04 | Mixer Circuit | Zachary Schneiderman | 2019-02-20 | This is the implementation of the clock generator to the mixers
2019-01-28 | Testing and benchmarking circuits | Zachary Schneiderman | 2019-03-20 | This task is verifying our project is meeting our goals in a more formalized task.
2019-01-28 | Implement RF Receive Code | James Bell | 2019-02-20 | This will be the completion of and testing of the Receving end of the radio
2019-02-04 | Speaker Circuit (Audio sheild -> Speaker) | Samual Hussey | 2019-02-20 | Making it be able to actually output audio
2019-02-04 | LCD for Teensy | James Bell | 2019-02-20 | Making a nice display for the current frequency
2019-02-04 | Encoder | Zachary Schneiderman | 2019-02-20 | This is the selection mechanism for the frequency
# items | Team Member
4 | James Bell
2 | Samual Hussey
3 | Zachary Schneiderman
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Closed Action Items
1.12 Software Defined Radio Open Action Items
2018-11-14 | Today's Date
Date | Description | DRI | Due By | #D | Notes / Comments
2018-08-31 | Gather contact information for each member of the team | James Bell | 2018-09-01 | - | CLOSED: It was done and we now have clear methods of communication
2018-08-31 | Create a github for repository of documentation and information | Zachary Schneiderman | 2018-09-10 | - | CLOSED: Done on 9/5/2018 and in use currently.
2018-08-31 | Rough draft of assigned sections in statement of work | James Bell | 2018-09-12 | - | CLOSED: Done on 9/12/2018.
2018-08-31 | Rough draft of assigned sections in statement of work | Samual Hussey | 2018-09-12 | - | CLOSED: Done on 9/12/2018.
2018-08-31 | Rough draft of assigned sections in statement of work | Zachary Schneiderman | 2018-09-12 | - | CLOSED: Done on 9/12/2018.
2018-08-31 | Watch and take notes of videos for SDR Prototype | James Bell | 2018-09-14 | - | CLOSED: Done on 9/14/2018.
2018-08-31 | Watch and take notes of videos for SDR Prototype | Samual Hussey | 2018-09-14 | - | CLOSED: Done on 9/14/2018.
2018-08-31 | Watch and take notes of videos for SDR Prototype | Zachary Schneiderman | 2018-09-14 | - | CLOSED: Done on 9/14/2018.
2018-09-12 | Organizing, and commenting pre-existing code for Prototype | James Bell | 2018-10-18 | - | CLOSED:
2018-09-12 | Schematics for Prototype in multi-sim or other such software | Samuel Hussey | 2018-10-22 | - | CLOSED: Completed for analog components we are biulding
2018-09-12 | List of components in Prototype priced and deliver estimates | Zachary Schneiderman | 2018-10-22 | - | CLOSED: Compiling list
2018-10-03 | Ordering Parts | James Bell | 2018-10-28 | - | CLOSED: Completed - Fill out and submit paperwork for ordering parts.
2018-10-24 | Updating simulations of analog components with most recent information from research | Samual Hussey | 2018-11-01 | - | Completed - Bandpass filters and RF amplifer.
2018-10-24 | Labor Cost Schedule | Samual Hussey | 2018-11-18 | - | This is a class deliverable, more details on weekly schedule
2018-10-24 | Labor Cost Schedule | James Bell | 2018-11-18 | - | This is a class deliverable, more details on weekly schedule
2018-10-24 | Labor Cost Schedule | Zachary Schneiderman | 2018-11-18 | - | This is a class deliverable, more details on weekly schedule
2018-10-24 | Labor Cost Schedule | Samual Hussey | 2018-11-18 | - | Completed -This is a class deliverable, more details on weekly schedule
2018-10-24 | Labor Cost Schedule | James Bell | 2018-11-18 | - | Completed -This is a class deliverable, more details on weekly schedule
2018-10-24 | Labor Cost Schedule | Zachary Schneiderman | 2018-11-18 | - | Completed -This is a class deliverable, more details on weekly schedule
2018-11-19 | Test plan portion | Samual Hussey | 2018-11-30 |  | Completed - More details on weekly project schedule
2018-11-19 | Test plan portion | James Bell | 2018-11-30 |  | Completed - More details on weekly project schedule
2018-11-19 | Test plan portion | Zachary Schneiderman | 2018-11-30 |  | Completed - More details on weekly project schedule
2018-11-05 | Senior design poster | Zachary Schneiderman | 2018-11-30 | - | Completed
2018-11-07 | Senior design notebook | James Bell | 2018-12-07 | - | Completed
2018-11-19 | Individual Report | Samual Hussey | 2018-12-03 | - | Completed - Required for the course
2018-11-19 | Individual Report | James Bell | 2018-12-03 |  | Completed - Required for the course
2018-11-19 | Individual Report | Zachary Schneiderman | 2018-12-03 |  | Completed - Required for the course
# items | Team Member
3 | James Bell
2 | Samual Hussey
3 | Zachary Schneiderman
0 | 0
Note on A2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Instructions and Lists
Team Members
James Bell
Samual Hussey
Zachary Schneiderman
The DRI field uses the Data > Data Validation function in Excel, this allows you to quickly select the team members names. Change the names above to match your team.
If you copy and paste the last action item it will likely mess up the formulas below. Try inserting a row above then pasting the last row into the added row.
You can use the Data > Sort & Filter > Filter function on the row headings if you want to sort by DRI or due date. Same issue applies as above, have to be careful about adding rows below areas that are used in formulas.
Having column A blank makes it easier to capture a screenshot to paste in weekly. Also you can go into view and turn off gridlines if you want a cleaner look.