## F'18
1.12 Software Defined Radio Milestone Schedule | [5 empty] | Notes
2019-04-17 | Last Update
20 | calendar days until Senior Design Day
DRI | Task | Dur | Start | End | Status
Samuel Hussey | Statement Of Work (Executive Summary) | 24 | 2018-08-31 | 2018-09-24 | Finished
Zachary Schneiderman | Statement Of Work (Buisness Need) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Statement Of Work (Product Scope Description) | 24 | 2018-08-31 | 2018-09-24 | Finished
Zachary Schneiderman | Statement Of Work (Project Scope Description) | 24 | 2018-08-31 | 2018-09-24 | Finished
Samuel Hussey | Statement Of Work (Sponser Support Elements) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Statement Of Work (Aprovals Signature) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Zachary Schneiderman | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Samuel Hussey | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Zachary Schneiderman | List of components in Prototype priced and deliver estimates | 40 | 2018-09-12 | 2018-10-22 | Finished
Samuel Hussey | Data/Signal Flow chart | 40 | 2018-09-12 | 2018-10-22 | Finished
Samuel Hussey | Schematics for Prototype in multi-sim or other such software | 40 | 2018-09-12 | 2018-10-22 | Finished
James Bell | Organizing, and commenting pre-existing code for Prototype | 33 | 2018-09-12 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.1 (Summary) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.2 (Sponser Requirments) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.3 (Existing System) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 1.4 (Terminology) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.1 (User Attributes and Use Cases) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.2 (Administration Functions) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.3 (Error Handling) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.4 (Saftey and Security) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.5 (Help and User Documentation) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.6.1 (User) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.6.2 (Software) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.6.3 (Hardware) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.6.4 (Mechanical) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.7 (Boundary Conditions and Constraints) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.8 (Performance) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.9 (Software Platforms) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.10 (Service, Support, & Maintence) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.11 (Expandability or Customization) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 3 (Project Alignment Matrix) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 4 (References) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 5 (Approvals) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | RF Amplifier Simulation v0.1 | 5 | 2018-10-10 | 2018-10-15 | Finished
James Bell | IDR Power Point | 12 | 2018-10-10 | 2018-10-22 | Finished
Zachary Schneiderman | RF Amplifier Biuld/ research, (redesign?) |  | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | Speaker Amplifier | 5 | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | Bandpass Filter Simulation | 5 | 2018-10-10 | 2018-10-15 | Finished
James Bell | Prep and do initial design review | 14 | 2018-10-15 | 2018-10-29 | Finished
James Bell | Order Parts | 4 | 2018-10-24 | 2018-10-28 | Finished
Samuel Hussey | All Siumulations Completed for analog components we are constructing | 8 | 2018-10-24 | 2018-11-01 | Finished
James Bell | Labor Cost Schedule Section 1 | 15 | 2018-11-04 | 2018-11-19 | Finished
James Bell | Labor Cost Schedule Section 2 | 15 | 2018-11-04 | 2018-11-19 | Finished
Zachary Schneiderman | Labor Cost Schedule Section 3 | 15 | 2018-11-04 | 2018-11-19 | Finished
Samuel Hussey | Labor Cost Schedule Section 4 | 15 | 2018-11-04 | 2018-11-19 | Finished
Zachary Schneiderman | Labor Cost Schedule Section 5 | 15 | 2018-11-04 | 2018-11-19 | Finished
James Bell | Labor Cost Schedule Section 6 | 15 | 2018-11-04 | 2018-11-19 | Finished
Zachary Schneiderman | Poster Draft | 21 | 2018-11-05 | 2018-11-26 | Finished
James Bell | Compile Senior design day notebook | 30 | 2018-11-07 | 2018-12-07 | Finished
| Thanksgiving Break | 4 | 2018-11-21 | 2018-11-25 | Finished
Zachary Schneiderman | Create Quadrature Converter | 21 | 2018-11-05 | 2018-11-26 | Finished
Zachary Schneiderman | Print Poster, Finalize Display | 16 | 2018-11-12 | 2018-11-28 | Finished
James Bell | Test Plan Overview (Section 1) | 11 | 2018-11-19 | 2018-11-30 | Finished
Samuel Hussey | Test Plan Features to be tested/not to be tested (Section 2) | 11 | 2018-11-19 | 2018-11-30 | Finished
Samuel Hussey | Testing Approach (Section 3) | 11 | 2018-11-19 | 2018-11-30 | Finished
Zachary Schneiderman | Test Cases (Section 4) | 11 | 2018-11-19 | 2018-11-30 | Finished
Samuel Hussey | Test Schedule (Section 5) | 11 | 2018-11-19 | 2018-11-30 | Finished
James Bell | Individual Reports Senior Design 1 | 14 | 2018-11-19 | 2018-12-03 | Finished
Zachary Schneiderman | Individual Reports Senior Design 1 | 14 | 2018-11-19 | 2018-12-03 | Finished
Samuel Hussey | Individual Reports Senior Design 1 | 14 | 2018-11-19 | 2018-12-03 | Finished
| Senior Design Day | 0 | 2018-12-07 | 2018-12-07 | Finished
James Bell | Combine Audio transformer and Low pass filter | 7 | 2019-01-28 | 2019-02-04 | Finished
Samuel Hussey | RF Splitter and combiner | 9 | 2019-01-28 | 2019-02-06 | Finished
Samuel Hussey | Bandpass Filters | 16 | 2019-01-28 | 2019-02-13 | Finished
Zachary Schneiderman | Mixer Circuit, (clock gen -> mixer) | 16 | 2019-02-04 | 2019-02-20 | Finished
Zachary Schneiderman | Test/Benchmark Circuits | 51 | 2019-01-28 | 2019-03-20 | Finished
James Bell | Implement RF Receive Code | 23 | 2019-01-28 | 2019-02-20 | Finished
Samuel Hussey | Speaker Circuit (Audio sheild -> Speaker) | 16 | 2019-02-04 | 2019-02-20 | Finished
James Bell | LCD for Teensy | 16 | 2019-02-04 | 2019-02-20 | Finished
Zachary Schneiderman | Encoder | 16 | 2019-02-04 | 2019-02-20 | Finished
James Bell | Progress Presentation | 12 | 2019-02-13 | 2019-02-25 | Finished
Zachary Schneiderman | Add licensing selection to radio code | 16 | 2019-02-25 | 2019-03-13 | Finished
Samuel Hussey | Relays for Transmit Receive control | 11 | 2019-02-25 | 2019-03-08 | Finished
Zachary Schneiderman | Band Selection in Code | 11 | 2019-02-25 | 2019-03-08 | Finished
James Bell | Audio Pass through test | 16 | 2019-02-25 | 2019-03-13 | Finished
Samuel Hussey | Add Relays and splitter/combiner to curcuit. | 22 | 2019-03-10 | 2019-04-01 | Finished
James Bell | Make testing signals for receive | 12 | 2019-03-20 | 2019-04-01 | Finished
Samuel Hussey | Test mixers for functionality | 5 | 2019-03-27 | 2019-04-01 | Finished
James Bell | find/rectify 14Hz offset in system | 5 | 2019-03-27 | 2019-04-01 | Finished
Zachary Schneiderman | add none burned out teensy to system | 7 | 2019-03-25 | 2019-04-01 | Finished
Samuel Hussey | Identify and correct toroid power problem | 6 | 2019-04-11 | 2019-04-17 | Finished
James Bell | Make Final Design Review Power Point | 3 | 2019-04-11 | 2019-04-14 | Finished
Zachary Schneiderman | Collect data for Final Design review | 3 | 2019-04-11 | 2019-04-14 | Finished
James Bell | Create SSB testing Signals | 5 | 2019-04-11 | 2019-04-16 | Finished
Zachary Schneiderman | Test SSB signals on radio receiver | 1 | 2019-04-16 | 2019-04-17 | Finished
Add microphone to audio sheild
Get transmit functionality in code
| Raspberry Pi implementation | 41 | 2019-01-22 | 2019-03-04 | Not Started
| Custom PCB | 41 | 2019-01-22 | 2019-03-04 | Not Started
| Higher Power Amplifier | 21 | 2019-02-19 | 2019-03-12 | Not Started
| Alternate Power Sources | 21 | 2019-02-19 | 2019-03-12 | Not Started
| Custom Cases | 28 | 2019-03-12 | 2019-04-09 | Not Started
| Head phone output jack | 27 | 2019-04-09 | 2019-05-06 | Not Started
James Bell | Finalize Poster | 14 | 2019-04-15 | 2019-04-29 | Not Started
| Print Poster, Finalize Display | 0 | 2019-05-03 | 2019-05-03 | Not Started
| Senior Design Day | 0 | 2019-05-07 | 2019-05-07 | Not Started
Names | Total Tasks In progress | Total Task Overdue |  |  | Total Tasks Finished | Total Tasks Not started | Total Tasks Critical
James Bell | 0 | 0 |  |  | 32 | 1 | 0
Samuel Hussey | 0 | 0 |  |  | 26 | 0 | 0
Zachary Schneiderman | 0 | 0 |  |  | 26 | 0 | 0
total tasks in system | 85
Task completed | 84
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.
Note on B4: Hinkle, Lee B: Designated Responsible Individual. Put the name of the team member responsible for the task here. If more then one, pick the lead person (or better yet divide the task further into individual tasks)
Note on C4: Hinkle, Lee B: Briefly describe the deliverable the DRI must provide back to the team. GOOD: Power Budget & Battery Recommendation BAD: Investigate Battery Technologies

## James Tasks Only (For D1 rprt)
1.12 Software Defined Radio Milestone Schedule (James Only)
2018-11-28 | Last Update
9 | calendar days until Senior Design Day
DRI | Task | Dur | Start | End | Status
James Bell | Statement Of Work (Product Scope Description) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Statement Of Work (Aprovals Signature) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
James Bell | Organizing, and commenting pre-existing code for Prototype | 33 | 2018-09-12 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.1 (Summary) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.2 (Sponser Requirments) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.3 (Existing System) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.4 (Saftey and Security) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.6.2 (Software) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.8 (Performance) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.9 (Software Platforms) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.10 (Service, Support, & Maintence) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.11 (Expandability or Customization) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 5 (Approvals) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | IDR Power Point | 12 | 2018-10-10 | 2018-10-22 | Finished
James Bell | Prep and do initial design review | 14 | 2018-10-15 | 2018-10-29 | Finished
James Bell | Order Parts | 4 | 2018-10-24 | 2018-10-28 | Finished
James Bell | Labor Cost Schedule Section 1 | 15 | 2018-11-04 | 2018-11-19 | Finished
James Bell | Labor Cost Schedule Section 2 | 15 | 2018-11-04 | 2018-11-19 | Finished
James Bell | Labor Cost Schedule Section 6 | 15 | 2018-11-04 | 2018-11-19 | Finished
James Bell | Test Plan Overview (Section 1) | 11 | 2018-11-19 | 2018-11-30 | Finished
Note on B3: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.
Note on B5: Hinkle, Lee B: Designated Responsible Individual. Put the name of the team member responsible for the task here. If more then one, pick the lead person (or better yet divide the task further into individual tasks)
Note on C5: Hinkle, Lee B: Briefly describe the deliverable the DRI must provide back to the team. GOOD: Power Budget & Battery Recommendation BAD: Investigate Battery Technologies

## Zachs Tasks Only (For D1 rprt)
1.12 Software Defined Radio Milestone Schedule (Zach only)
2018-11-28 | Last Update
9 | calendar days until Senior Design Day
DRI | Task | Dur | Start | End | Status
Zachary Schneiderman | Statement Of Work (Buisness Need) | 24 | 2018-08-31 | 2018-09-24 | Finished
Zachary Schneiderman | Statement Of Work (Project Scope Description) | 24 | 2018-08-31 | 2018-09-24 | Finished
Zachary Schneiderman | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Zachary Schneiderman | List of components in Prototype priced and deliver estimates | 40 | 2018-09-12 | 2018-10-22 | Finished
Zachary Schneiderman | Functional Spec section 1.4 (Terminology) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.1 (User Attributes and Use Cases) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.5 (Help and User Documentation) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.6.1 (User) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.7 (Boundary Conditions and Constraints) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 4 (References) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | RF Amplifier Biuld/ research, (redesign?) |  | 2018-10-10 | 2018-10-15 | Finished
Zachary Schneiderman | Bandpass Filter and Radio Frequeny Amplifier built | 14 | 2018-10-24 | 2018-11-07 | Finished
Zachary Schneiderman | Labor Cost Schedule Section 3 | 15 | 2018-11-04 | 2018-11-19 | Finished
Zachary Schneiderman | Labor Cost Schedule Section 5 | 15 | 2018-11-04 | 2018-11-19 | Finished
Zachary Schneiderman | Poster Draft | 21 | 2018-11-05 | 2018-11-26 | Finished
Zachary Schneiderman | Print Poster, Finalize Display | 16 | 2018-11-12 | 2018-11-28 | Finished
Note on B3: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.
Note on B5: Hinkle, Lee B: Designated Responsible Individual. Put the name of the team member responsible for the task here. If more then one, pick the lead person (or better yet divide the task further into individual tasks)
Note on C5: Hinkle, Lee B: Briefly describe the deliverable the DRI must provide back to the team. GOOD: Power Budget & Battery Recommendation BAD: Investigate Battery Technologies

## Samual Tasks Only (for D1 rprt)
1.12 Software Defined Radio Milestone Schedule (Samual Only)
2018-11-28 | Last Update
9 | calendar days until Senior Design Day
DRI | Task | Dur | Start | End | Status
Samuel Hussey | Statement Of Work (Executive Summary) | 24 | 2018-08-31 | 2018-09-24 | Finished
Samuel Hussey | Statement Of Work (Sponser Support Elements) | 24 | 2018-08-31 | 2018-09-24 | Finished
Samuel Hussey | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Samuel Hussey | Data/Signal Flow chart | 40 | 2018-09-12 | 2018-10-22 | Finished
Samuel Hussey | Schematics for Prototype in multi-sim or other such software | 40 | 2018-09-12 | 2018-10-22 | Finished
James Bell | Organizing, and commenting pre-existing code for Prototype | 33 | 2018-09-12 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.2 (Administration Functions) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.3 (Error Handling) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.6.3 (Hardware) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.6.4 (Mechanical) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 3 (Project Alignment Matrix) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | RF Amplifier Simulation v0.1 | 5 | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | Speaker Amplifier | 5 | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | Bandpass Filter Simulation | 5 | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | All Siumulations Completed for analog components we are constructing | 8 | 2018-10-24 | 2018-11-01 | Finished
Samuel Hussey | Labor Cost Schedule Section 4 | 15 | 2018-11-04 | 2018-11-19 | Finished
Note on B3: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.
Note on B5: Hinkle, Lee B: Designated Responsible Individual. Put the name of the team member responsible for the task here. If more then one, pick the lead person (or better yet divide the task further into individual tasks)
Note on C5: Hinkle, Lee B: Briefly describe the deliverable the DRI must provide back to the team. GOOD: Power Budget & Battery Recommendation BAD: Investigate Battery Technologies

## Fields
Status
Not Started
In progress
Late
Overdue
Critical
Finished