## F'18
1.12 Software Defined Radio Milestone Schedule | [5 empty] | Notes
2018-11-14 | Last Update
23 | calendar days until Senior Design Day
DRI | Task | Dur | Start | End | Status
Samuel Hussey | Statement Of Work (Executive Summary) | 24 | 2018-08-31 | 2018-09-24 | Finished
Zachary Schneiderman | Statement Of Work (Buisness Need) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Statement Of Work (Product Scope Description) | 24 | 2018-08-31 | 2018-09-24 | Finished
Zachary Schneiderman | Statement Of Work (Project Scope Description) | 24 | 2018-08-31 | 2018-09-24 | Finished
Samuel Hussey | Statement Of Work (Sponser Support Elements) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Statement Of Work (Aprovals Signature) | 24 | 2018-08-31 | 2018-09-24 | Finished
James Bell | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Zachary Schneiderman | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Samuel Hussey | Watch and take notes on Videos of SDR | 14 | 2018-08-31 | 2018-09-14 | Finished
Zachary Schneiderman | List of components in Prototype priced and deliver estimates | 40 | 2018-09-12 | 2018-10-22 | Finished
Samuel Hussey | Data/Signal Flow chart | 40 | 2018-09-12 | 2018-10-22 | Finished
Samuel Hussey | Schematics for Prototype in multi-sim or other such software | 40 | 2018-09-12 | 2018-10-22 | Finished
James Bell | Organizing, and commenting pre-existing code for Prototype | 33 | 2018-09-12 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.1 (Summary) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.2 (Sponser Requirments) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 1.3 (Existing System) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 1.4 (Terminology) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.1 (User Attributes and Use Cases) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.2 (Administration Functions) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.3 (Error Handling) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.4 (Saftey and Security) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.5 (Help and User Documentation) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.6.1 (User) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.6.2 (Software) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.6.3 (Hardware) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 2.6.4 (Mechanical) | 14 | 2018-10-01 | 2018-10-15 | Finished
Zachary Schneiderman | Functional Spec section 2.7 (Boundary Conditions and Constraints) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell (Team) | Functional Spec section 2.8 (Performance) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.9 (Software Platforms) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.10 (Service, Support, & Maintence) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 2.11 (Expandability or Customization) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | Functional Spec section 3 (Project Alignment Matrix) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell (Team) | Functional Spec section 4 (References) | 14 | 2018-10-01 | 2018-10-15 | Finished
James Bell | Functional Spec section 5 (Approvals) | 14 | 2018-10-01 | 2018-10-15 | Finished
Samuel Hussey | RF Amplifier Simulation v0.1 | 5 | 2018-10-10 | 2018-10-15 | Finished
James Bell | IDR Power Point | 12 | 2018-10-10 | 2018-10-22 | Finished
Zachary Schneiderman | RF Amplifier Biuld/ research, (redesign?) |  | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | Speaker Amplifier | 5 | 2018-10-10 | 2018-10-15 | Finished
Samuel Hussey | Bandpass Filter Simulation | 5 | 2018-10-10 | 2018-10-15 | Finished
James Bell | Prep and do initial design review | 14 | 2018-10-15 | 2018-10-29 | Finished
James Bell | Order Parts | 4 | 2018-10-24 | 2018-10-28 | Finished
Samuel Hussey | All Siumulations Completed for analog components we are constructing | 8 | 2018-10-24 | 2018-11-01 | Finished
Zachary Schneiderman | Bandpass Filter and Radio Frequeny Amplifier built | 14 | 2018-10-24 | 2018-11-07 | Overdue | Can not build band pass filter without torroids
James Bell | Labor Cost Schedule Section 1 | 15 | 2018-11-04 | 2018-11-19 | In progress
James Bell | Labor Cost Schedule Section 2 | 15 | 2018-11-04 | 2018-11-19 | In progress
Zachary Schneiderman | Labor Cost Schedule Section 3 | 15 | 2018-11-04 | 2018-11-19 | In progress
Samuel Hussey | Labor Cost Schedule Section 4 | 15 | 2018-11-04 | 2018-11-19 | In progress
Zachary Schneiderman | Labor Cost Schedule Section 5 | 15 | 2018-11-04 | 2018-11-19 | In progress
James Bell | Labor Cost Schedule Section 6 | 15 | 2018-11-04 | 2018-11-19 | In progress
Zachary Schneiderman | Poster Draft | 21 | 2018-11-05 | 2018-11-26 | In progress
James Bell | Compile Senior design day notebook | 30 | 2018-11-07 | 2018-12-07 | In progress
| Test/Benchmark Circuits | 14 | 2018-11-05 | 2018-11-19 | Not Started
| Develop Passthrough Tests | 14 | 2018-11-05 | 2018-11-19 | Not Started
| Create Quadrature Converter | 21 | 2018-11-05 | 2018-11-26 | Finished
James Bell | Test Plan Overview (Section 1) | 11 | 2018-11-19 | 2018-11-30 | In progress
James Bell | Test Plan Features to be tested/not to be tested (Section 2) |  | 2018-11-19 | 2018-11-30 | In progress
Samuel Hussey | Testing Approach (Section 3) |  | 2018-11-19 | 2018-11-30 | In progress
Zachary Schneiderman | Test Cases (section 4) |  | 2018-11-19 | 2018-11-30 | In progress
Samuel Hussey | Test Schedule |  | 2018-11-19 | 2018-11-30 | In progress
James Bell | Individual Reports Senior Design 1 |  | 2018-11-19 | 2018-12-03 | In progress
Zachary Schneiderman | Individual Reports Senior Design 1 |  | 2018-11-19 | 2018-12-03 | In progress
Samuel Hussey | Individual Reports Senior Design 1 |  | 2018-11-19 | 2018-12-03 | In progress
| Configure LCD/Tuner Knob | 13 | 2018-11-19 | 2018-12-02 | Not Started
| Implement RF Receive Code | 7 | 2018-11-19 | 2018-11-26 | Not Started
| Thanksgiving Break | 4 | 2018-11-21 | 2018-11-25 | Not Started
| Receive/Tune tests | 9 | 2018-11-26 | 2018-12-05 | Not Started
| Receive/Tune tests | 9 | 2018-11-26 | 2018-12-05 | Not Started
| Print Poster, Finalize Display | 16 | 2018-11-12 | 2018-11-28 | Not Started
| Transmitting/Tune tests | 9 | 2018-11-26 | 2018-12-05 | Not Started
| Senior Design Day | 0 | 2018-12-07 | 2018-12-07 | Not Started
| Add licensing selection to radio | 28 | 2019-01-22 | 2019-02-19 | Not Started
| Raspberry Pi implementation | 41 | 2019-01-22 | 2019-03-04 | Not Started
| Custom PCB | 41 | 2019-01-22 | 2019-03-04 | Not Started
| Higher Power Amplifier | 21 | 2019-02-19 | 2019-03-12 | Not Started
| Alternate Power Sources | 21 | 2019-02-19 | 2019-03-12 | Not Started
| Custom Cases | 28 | 2019-03-12 | 2019-04-09 | Not Started
| Head phone output jack | 27 | 2019-04-09 | 2019-05-06 | Not Started
| Finalize Poster | 0 |  |  | Not Started
| Print Poster, Finalize Display | 0 |  |  | Not Started
| Senior Design Day |  |  |  | Not Started
Names | Total Tasks In progress | Total Task Overdue |  |  | Total Tasks Finished | Total Tasks Not started | Total Tasks Critical
James Bell | 7 | 0 |  |  | 16 | 0 | 0
Samuel Hussey | 4 | 0 |  |  | 14 | 0 | 0
Zachary Schneiderman | 5 | 1 |  |  | 10 | 0 | 0
"Team" tasks (To do in adhoc meetings | 0 | 0 |  |  | 2 | 0 | 0
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.
Note on B4: Hinkle, Lee B: Designated Responsible Individual. Put the name of the team member responsible for the task here. If more then one, pick the lead person (or better yet divide the task further into individual tasks)
Note on C4: Hinkle, Lee B: Briefly describe the deliverable the DRI must provide back to the team. GOOD: Power Budget & Battery Recommendation BAD: Investigate Battery Technologies

## Fields
Status
Not Started
In progress
Late
Overdue
Critical
Finished