## Sheet1
Task | DRI | Duration, Weeks | Start | End
Statement of Work (Executive Summary) | Samuel Hussey | 21 | 2018-08-31 | 2018-09-24
Watch and take notes on Videos of SDR | All | 24 | 2018-08-31 | 2018-09-24
Complete Parts List | Zachary Schneiderman | 18 | 2018-09-24 | 2018-10-18
Setup Arduino Environment and establish understanding the prototype code | James Bell | 18 | 2018-09-24 | 2018-10-18
Complete Functional Specs | Samuel Hussey | 18 | 2018-09-24 | 2018-10-01
Signed Spec Sheet | James Bell | 24 | 2018-10-10 | 2018-11-05
Begin RF Amplifier |  | 21 | 2018-10-10 | 2018-11-05
Begin Power Amp |  | 21 | 2018-10-10 | 2018-11-05
Begin Bandpass Filter |  | 21 | 2018-10-10 | 2018-11-05
Labor Cost Schedule | James Bell | 14 | 2018-11-05 | 2018-11-19
Poster Draft | James Bell | 21 | 2018-11-05 | 2018-11-26
Test/Benchmark Circuits |  | 14 | 2018-11-05 | 2018-11-19
Develop Passthrough Tests |  | 14 | 2018-11-05 | 2018-11-19
Create Quadrature Converter |  | 21 | 2018-11-05 | 2018-11-26
Test Plan | James Bell | 10 | 2018-11-19 | 2018-11-30
Configure LCD/Tuner Knob |  | 14 | 2018-11-19 | 2018-12-02
Implement RF Receive Code |  | 7 | 2018-11-19 | 2018-11-26
Receive/Tune tests |  | 10 | 2018-11-26 | 2018-12-05
Transmitting/Tune tests |  | 10 | 2018-11-26 | 2018-12-05
Final Preparations for Senior design day |  | 7 | 2018-12-05 | 2018-12-07
Add licensing selection to radio |  | 28 | 2019-01-22 | 2019-02-19
Raspberry Pi implementation |  | 42 | 2019-01-22 | 2019-03-04
Custom PCB |  | 42 | 2019-01-22 | 2019-03-04
Higher Power Amplifier |  | 28 | 2019-02-19 | 2019-03-12
Alternate Power Sources |  | 28 | 2019-02-19 | 2019-03-12
Custom Cases |  | 28 | 2019-03-12 | 2019-04-09
Head phone output jack |  | 28 | 2019-04-09 | 2019-05-06